## Tabelle1
Projectplan: GROUP 3
Date | KW 43 | KW 44 | KW 45 | KW 46 | KW 47 | KW 48 | KW 49 | KW 50 | KW 51 (Weihnachten) | KW 52 (Silvester) | KW 1 | KW 2 | KW 3 | KW 4 | KW 5
Milestones
Kickoff | bar: KW 43
Sensor node
OS for Raspberry | bar: KW 44
Connect and access camera | bar: KW 45
Application | bar: KW 45 to KW 48
Machine Learning
Collect Data | bar: KW 44 to KW 45
Label data (labeIMG) | bar: KW 46 to KW 47
Choose Framework | bar: KW 44 to KW 45
Train Model | bar: KW 47 to KW 48
Validate Model | bar: KW 49
Run Model on Sensor node | bar: KW 49 to KW 50
Cluster
OS Kubernetics cluster | bar: KW 44
Connect Cluster Raspberries | bar: KW 45 to KW 46
Setup storaging of Images | bar: KW 47 to KW 48
GUI | bar: KW 50
Store Metadata in LOG-file/database | bar: KW 49
Send Images via Telegramm? (optional)
Network
Connect Sensore node and cluster | bar: KW 47 to KW 48
Define Interface | bar: KW 45
Testing
Test camera with ML Framework | bar: KW 46
Test full system
Documentation