## Tabelle1
Projectplan: GROUP 3
Date | KW 43 | KW 44 | KW 45 | KW 46 | KW 47 | KW 48 | KW 49 | KW 50 | KW 51 (Weihnachten) | KW 52 (Silvester) | KW 1 | KW 2 | KW 3 | KW 4 | KW 5
Milestones
Kickoff | bar: KW 43
Sensor node
OS for Raspberry | bar: KW 44
Connect and access camera | bar: KW 45
Application | bar: KW 45 to KW 48
Machine Learning
Collect Data | KW 44: ca 1000 Pic: Lucas Sister -> sort out video frames, 500 pic: from previous students
Label data (labeIMG) | KW 46: data was labeld with roboflow
Choose Framework | KW 44: yolov5 was choosen, source: https://peerj.com/preprints/27880.pdf
Train Model | KW 47: Trainig of a Model has been completed, optimization needed, check for overfitting
Validate Model | bar: KW 49
Run Model on Sensor node | bar: KW 49 to KW 50
Cluster
OS Kubernetics cluster | bar: KW 44
Connect Cluster Raspberries | bar: KW 45 to KW 46
Setup storaging of Images | bar: KW 47 to KW 48
GUI | bar: KW 50
Store Metadata in LOG-file/database | bar: KW 49
Send Images via Telegramm? (optional)
Network
Connect Sensore node and cluster | bar: KW 47 to KW 48
Define Interface | bar: KW 45
Testing
Test camera with ML Framework | bar: KW 46
Test full system
Documentation